## Sheet1
Estimate |  | Siliguri Municipal Corporation
|  | Estimate for: | [8 empty] | Construction
Construction of Public Toilet at Naukaghat More, Ward no.- 31
All Linear measurements are in metre
Schedule ref. | Item Number | Description of Item |  |  |  |  | Quantity |  | Rate | Unit | Amount Rs.
|  | Member | Number | Length | Breadth | Height
.
PWD(WB)/BUILDING WORKS/Page-1/Item-2
1.2 | 1 | Earth work in excavation of foundation trenches or drains in all sorts of soil (including mixed soil but excluding laterite or sand stone) including removing, spreading or stacking the spoils within a lead of 75m. as directed. The item includes necessary trimming the sides of trenches, levelling, dressing and ramming the bottom, bailing out water as required complete. .
1.2.a | 1.01 | (a) Depth of excavation not exceeding 1.500 mm.
|  |  | 6 | 1.35 | 1.35 | 1.125 | 12.302 | Cu.M
|  |  | 2 | 4.85 | 0.35 | 0.425 | 1.443 | Cu.M
|  |  | 3 | 4.3 | 0.35 | 0.475 | 2.145 | Cu.M
|  |  | 1 | 7.25 | 0.25 | 0.425 | 0.77 | Cu.M
|  |  | 1 | 1.835 | 2.1 | 1.5 | 5.78 | Cu.M
[6 empty] | Total | 22.44 | Cu.M | 11927 | % Cu.M. | 2676.42
PWD(WB)/BUILDING WORKS/Page-1/Item-2
1.2 | 2 | Earth work in excavation of foundation trenches or drains in all sorts of soil (including mixed soil but excluding laterite or sand stone) including removing, spreading or stacking the spoils within a lead of 75m. as directed. The item includes necessary trimming the sides of trenches, levelling, dressing and ramming the bottom, bailing out water as required complete. .
1.2.b | 2.01 | (b) Depth of excavation additional depth beyond 1,500 mm. and up to 3,000 mm. but not requiring shoring.
|  |  | 1 | 1.835 | 2.1 | 0.176 | 0.678 | Cu.M
[6 empty] | Total | 0.678 | Cu.M | 19238 | % Cu.M. | 130.43
PWD(WB)/BUILDING WORKS/Page-14/Item-1
14.1 | 3 | Single brick flat soling of picked jhama bricks including ramming and dressing bed to proper level and filling joints with local sand.
|  |  | 6 | 1.35 | 1.35 |  | 10.935 | Sq.M
|  |  | 2 | 4.8 | 0.35 |  | 3.36 | Sq.M
|  |  | 3 | 4.3 | 0.35 |  | 4.515 | Sq.M
|  |  | 1 | 7.25 | 0.25 |  | 1.813 | Sq.M
|  |  | 1 | 4.35 | 4.05 |  | 17.618 | Sq.M
|  |  | 1 | 4 | 1 |  | 4 | Sq.M
|  |  | 1 | 1.835 | 2.1 |  | 3.854 | Sq.M
[6 empty] | Total | 46.095 | Sq.M | 324 | Sq.M. | 14934.78
PWD(WB)/BUILDING WORKS/Page-24/Item-4
24.4 | 4 | Ordinary cement concrete (mix 1:2:4) with graded stone chips (20 mm nominal size) excluding shuttring and reinforcement, if any, in ground floor as per relevant IS codes.
24.4.b | 4.01 | (b) River bazree.
|  |  | 6 | 1.2 | 1.2 | 0.1 | 0.864 | Cu.M
|  |  | 2 | 4.85 | 0.25 | 0.075 | 0.182 | Cu.M
|  |  | 3 | 4.3 | 0.25 | 0.075 | 0.242 | Cu.M
|  |  | 1 | 7.25 | 0.25 | 0.075 | 0.136 | Cu.M
|  |  | 1 | 4.35 | 4.05 | 0.075 | 1.321 | Cu.M
|  |  | 1 | 4 | 1 | 0.075 | 0.3 | Cu.M
|  |  | 2 | 5.1 | 0.45 | 0.075 | 0.344 | Cu.M
|  |  | 2 | 4.55 | 0.45 | 0.075 | 0.307 | Cu.M
[6 empty] | Total | 3.696 | Cu.M | 4006 | Cu.M | 14806.18
PWD(WB)/BUILDING WORKS/Page-47/Item-2
47.2 | 5 | 25 mm. thick damp proof with cement concrete (1:1.5:3) (withgraded stone aggregate 10 mm. normal size) and painting thetop surface with a coat of bitumen [VG.40 ] using 1.7 kg. persq.m. including heating the bitumen and cost and carriage ofall materials complete. [Bitument to be supplied by theAgency]
|  |  | 2 | 4.85 | 0.25 |  | 2.425 | Sq.M
|  |  | 3 | 4.3 | 0.25 |  | 3.225 | Sq.M
|  |  | 1 | 7.25 | 0.125 |  | 0.906 | Sq.M
[6 empty] | Total | 6.556 | Sq.M | 269 | Sq.M. | 1763.56
PWD(WB)/BUILDING WORKS/Page-15/Item-8
15.8 | 6 | Brick work with 1st class bricks in cement mortar (1:6)
15.8.a | 6.01 | In foundation and plinth
|  |  | 1 | 22.6 | 0.25 | 0.6 | 3.39 | Cu.M
|  |  | 1 | 6 | 0.25 | 0.3 | 0.45 | Cu.M
|  |  | 1 | 6.4 | 0.25 | 1.7 | 2.72 | Cu.M
[6 empty] | Total | 6.56 | Cu.M | 4896 | Cum. | 32117.76
PWD(WB)/BUILDING WORKS/Page-15/Item-8
15.8 | 7 | Brick work with 1st class bricks in cement mortar (1:6)
15.8.b | 7.01 | In Super structure, ground floor.
|  |  | 2 | 4.35 | 0.25 | 2.7 | 5.873 | Cu.M
|  |  | 3 | 4.05 | 0.25 | 2.6 | 7.898 | Cu.M
|  |  | -1 | 2.05 | 0.25 | 2.1 | -1.076 | Cu.M
|  |  | -10 | 0.6 | 0.25 | 0.45 | -0.675 | Cu.M
[6 empty] | Total | 12.02 | Cu.M | 5119 | Cum. | 61530.38
PWD(WB)/BUILDING WORKS/Page-16/Item-16
16.16 | 8 | 125 mm. thick brick work with 1st class bricks in cement mortar (1:4) in ground floor.
|  |  | 1 | 7.25 | 2.725 |  | 19.756 | Sq.M
|  |  | -3 | 0.75 | 1.95 |  | -4.388 | Sq.M
|  |  | 1 | 21.7 | 0.3 |  | 6.51 | Sq.M
|  |  | 1 | 3.725 | 0.3 |  | 1.118 | Sq.M
[6 empty] | Total | 22.996 | Sq.M | 674 | Sq.M. | 15499.3
PWD(WB)/BUILDING WORKS/Page-1/Item-3
1.3 | 9 | Earth work in filling in foundation trenches or plinth with good earth in layers not exceeding 150 mm. including watering and ramming etc.layer by layer complete .(payment to be made on the basis of measurement of finished quantity of work).
1.3.a | 9.01 | (a) With earth obtained from excavation of foundation.
|  |  | 1 | 0.66 | 18.83 | 1 | 12.428 | Cu.M
[6 empty] | Total | 12.428 | Cu.M | 7754 | % Cu.M. | 963.67
PWD(WB)/BUILDING WORKS/Page-2/Item-4A
2.4A | 10 | (A) Filling in foundation or plinth by silver sand in layers not exceeding 150 mm. as directed and consolidating same by thorough saturation with water ramming complete . Including the cost of supply of sand .(payment to be made on measurement of finished quantity).
|  |  | 1 | 4.35 | 4.05 | 0.6 | 10.571 | Cu.M
|  |  | 1 | 4 | 1 | 0.225 | 0.9 | Cu.M
[6 empty] | Total | 11.471 | Cu.M | 52107 | % Cu.M. | 5977.19
PWD(WB)/BUILDING WORKS/Page-42/Item-36
42.36 | 11 | Hire and labour charge for shuttering with centreing and necessary staging up to 4 m. using approved stout props and thick hard wood planks of approved thick ness with required bracing for concrete slabs, beams, columns, lintels curved or staight including fitting fixing and striking out after complection of works. (up to roof of ground floor).
43.36.f | 11.01 | (f) 25mm. To 30mm. Shuttering with out staging in foundation etc.
|  |  | 6 | 4.8 | 0.2 |  | 5.76 | Sq.M
|  |  | 6 | 1.6 | 0.3 |  | 2.88 | Sq.M
|  |  | 4 | 4.85 | 0.25 |  | 4.85 | Sq.M
|  |  | 6 | 4.3 | 0.3 |  | 7.74 | Sq.M
|  |  | 2 | 7.25 | 0.25 |  | 3.625 | Sq.M
|  |  | 1 | 6 | 0.125 |  | 0.75 | Sq.M
|  |  | 1 | 1.2 | 1.5 |  | 1.8 | Sq.M
[6 empty] | Total | 27.405 | Sq.M | 205 | Sq.M. | 5618.03
PWD(WB)/BUILDING WORKS/Page-42/Item-36
42.36 | 12 | Hire and labour charge for shuttering with centreing and necessary staging up to 4 m. using approved stout props and thick hard wood planks of approved thick ness with required bracing for concrete slabs, beams, columns, lintels curved or staight including fitting fixing and striking out after complection of works. (up to roof of ground floor).
42.36.a | 12.01 | (a) 25 mm. to 30 mm. thick wooden shuttering as per decision & direction of the Engineer-in-charge. .
|  |  | 6 | 1 | 3.475 |  | 20.85 | Sq.M
|  |  | 4 | 4.6 | 0.175 |  | 3.22 | Sq.M
|  |  | 6 | 4.05 | 0.275 |  | 6.683 | Sq.M
|  |  | 2 | 23.85 | 0.15 |  | 7.155 | Sq.M
|  |  | 2 | 7 | 0.15 |  | 2.1 | Sq.M
|  |  | 10 | 0.45 | 0.3 |  | 1.35 | Sq.M
|  |  | 1 | 5.7 | 5.15 |  | 29.355 | Sq.M
|  |  | 1 | 21.7 | 0.125 |  | 2.713 | Sq.M
|  |  | 1 | 1 | 1.5 |  | 1.5 | Sq.M
[6 empty] | Total | 74.926 | Sq.M | 328 | Sq.M. | 24575.73
PWD(WB)/BUILDING WORKS/Page-26/Item-10
26.10 | 13 | Ordinary cement concrete (mix 1:1.5:3) with graded stone chips (20mm nominal size) excluding shuttering and reinforcement, if any, in ground floor as per relevant codes.
26.10.ii | 13.01 | (ii) River bazree.
|  |  | 6 | 1.2 | 1.2 | 0.2 | 1.728 | Cu.M
|  |  | 6 | 0.8 | 0.8 | 0.2 | 0.768 | Cu.M
|  |  | 6 | 0.4 | 0.4 | 0.3 | 0.288 | Cu.M
|  |  | 6 | 0.25 | 0.25 | 3.475 | 1.303 | Cu.M
|  |  | 2 | 5.1 | 0.25 | 0.25 | 0.638 | Cu.M
|  |  | 3 | 4.55 | 0.25 | 0.25 | 0.853 | Cu.M
|  |  | 1 | 7.25 | 0.25 | 0.25 | 0.453 | Cu.M
|  |  | 1 | 23.85 | 0.25 | 0.15 | 0.894 | Cu.M
|  |  | 1 | 23.85 | 0.25 | 0.15 | 0.894 | Cu.M
|  |  | 1 | 7 | 0.125 | 0.15 | 0.131 | Cu.M
|  |  | 10 | 0.45 | 0.3 | 0.075 | 0.101 | Cu.M
|  |  | 2 | 4.35 | 0.25 | 0.175 | 0.381 | Cu.M
|  |  | 3 | 4.05 | 0.25 | 0.275 | 0.835 | Cu.M
|  |  | 1 | 5.7 | 5.05 | 0.125 | 3.598 | Cu.M
|  |  | 2 | 2.4 | 0.6 | 0.075 | 0.216 | Cu.M
|  |  | 1 | 1.7 | 2 | 0.125 | 0.425 | Cu.M
|  |  | 1 | 1.7 | 2 | 0.125 | 0.425 | Cu.M
[6 empty] | Total | 13.931 | Cu.M | 4745 | Cu.M | 66102.6
PWD(WB)/BUILDING WORKS/Page-43/Item-40
43.40 | 14 | Reinforcement for reinforced concrete work in all sorts of structures including distribution bars, stirrups, binders etc. initial straightening and removal of loose rust (if necessary), cutting to requisite length, hooking and bending to correct shape, placing in proper position and binding with 16 gauge black annealed wire at inter-section, complete as per drawing and direction.
44.40.a | 14.01 | (a) For works in foundation, basement and up to roof of ground floor/up to 4m. Tor steel/Mild steel.
44.40.a.i | 14.02 | SAIL/ TATA/RINL
Volumetric percentage calculation of reinforcefment
|  | Total volume |  |  |  |  | 13.931 | cum
|  | Percentage of steel |  | 1.5 | %
|  | Weight of steel |  | 7.85 | MT/cum | Total
|  | Reinforcement by volume of CC | (13.931.00*1.5*7.85)/100 |  |  |  | 1.64 | MT
[6 empty] | Total | 1.64 | MT | 66502 | M.T. | 109063.28
PWD(WB)/BUILDING WORKS/Page-48/Item-6
48.6 | 15 | Artificial stone in floor, dado, staircase etc. with cement conctrete (1:2:4) with stone chips laid in panels as directed with topping made with ordinary or white cement (as necessary) and marble dust in proportion (1:2) including smooth finishing and rounding off corners including raking out joints or roughening of concrete surface and application of cement slurry before flooring works, using cement @ 1.75 kg./sq.m. all complete including all materials and labour In ground floor. 3 mm. thick topping (High polishing grinding on this item is not permitted) with ordinary cement. Using grey cement.
48.6.ii | 15.01 | (ii) 25 mm. thick.
|  |  | 1 | 5.7 | 5.05 |  | 28.785 | Sq.M
[6 empty] | Total | 28.785 | Sq.M | 270 | Sq.M. | 7771.95
PWD(WB)/BUILDING WORKS/Page-192/Item-15
192.15 | 16 | Neat cement punning about 1.5mm thick in wall, dado, windowsill, floor etc.NOTE:Cement 0.152 cu.m per100 sq.m.
|  |  | 1 | 19.3 | 0.6 |  | 11.58 | Sq.M
|  |  | 1 | 5.4 | 1.7 |  | 9.18 | Sq.M
[6 empty] | Total | 20.76 | Sq.M | 34 | Sq.M. | 705.84
PWD(WB)/BUILDING WORKS/Page-189/Item-1
189.1 | 17 | Plaster ( to wall, floor, ceiling etc.) with sand and cement mortar including rounding off or chamfering conrners as directed and raking out joints including throating, nosing and drip course, scaffolding/staging where necessary (ground floor). [Excluding cost of chipping over concrete surface].
189.1.i | 17.01 | (i) with 1:6 cement mortar.
189.1.i.c | 17.02 | (c)15 mm. thick plaster.
|  |  | 2 | 5.1 | 3.9 |  | 39.78 | Sq.M
|  |  | 2 | 4.55 | 3.9 |  | 35.49 | Sq.M
|  |  | 20 | 0.45 | 0.3 |  | 2.7 | Sq.M
|  |  | 10 | 1.05 | 0.075 |  | 0.788 | Sq.M
|  |  | 4 | 4.55 | 2.875 |  | 52.325 | Sq.M
|  |  | 2 | 5.1 | 2.875 |  | 29.325 | Sq.M
|  |  | 6 | 1.2 | 2.875 |  | 20.7 | Sq.M
|  |  | 2 | 2.5 | 2.875 |  | 14.375 | Sq.M
|  |  | 1 | 1.6 | 2.875 |  | 4.6 | Sq.M
|  |  | -4 | 0.75 | 2.1 |  | -6.3 | Sq.M
|  |  | -1 | 2.05 | 2.1 |  | -4.305 | Sq.M
|  |  | -10 | 0.45 | 0.3 |  | -1.35 | Sq.M
|  |  | 1 | 19.8 | 0.975 |  | 19.305 | Sq.M
|  |  | 1 | 5.4 | 1.7 |  | 9.18 | Sq.M
[6 empty] | Total | 216.613 | Sq.M | 141 | Sq.M. | 30542.43
PWD(WB)/BUILDING WORKS/Page-189/Item-1
189.1 | 18 | Plaster ( to wall, floor, ceiling etc.) with sand and cement mortar including rounding off or chamfering conrners as directed and raking out joints including throating, nosing and drip course, scaffolding/staging where necessary (ground floor). [Excluding cost of chipping over concrete surface].
189.1.ii | 18.01 | (ii) With 1:4 cement mortar .
189.1.ii.c | 18.02 | (c)10 mm. thick plaster.
|  |  | 1 | 5.4 | 4.85 |  | 26.19 | Sq.M
[6 empty] | Total | 26.19 | Sq.M | 126 | Sq.M. | 3299.94
PWD(WB)/BUILDING WORKS/Page-115/Item-3
115.3 | 19 | Supplying, fitting and fixing fibre reinforced polymer (FRP) Composite doorframe as per approved section with glass fibre reinforced plastic moulded skinsand a special sandwich core, so as to impart monolitaheic composite structure asper approved technology of Department of Science and Technology (DST) tosafisfy IS: 4020 door testing performance criteria..
115.3.i | 19.01 | (i) 66mm x 90mm
|  |  | 4 | 4.95 |  |  | 19.8 | M
[6 empty] | Total | 19.8 | M | 497 | Mtr. | 9840.6
PWD(WB)/BUILDING WORKS/Page-125/Item-14
125.14 | 20 | Supplying, fitting & fixing fibre reinforced polymer (FRP) Composite doorshutters as per approved design with glass fibre reinforced plastic moulded skinsand a special sandwich core, so as to impart monolitaheic composite structure asper approved technology of Department of Science and Technology (DST) tosatisfy IS:4020 door testing performance criteria.In ground floor.
125.14.i | 20.01 | (i) 32 mm thick
|  |  | 4 | 2.1 | 0.75 |  | 6.3 | Sq.M
[6 empty] | Total | 6.3 | Sq.M | 2763 | Sq.M. | 17406.9
PWD(WB)/BUILDING WORKS/Page-144/Item-26
144.26 | 21 | Anodise aluminium barred/tower/socket bolt (full covered) of approved manufactured from extruded section conforming to I.S.204/74 fitted and Fixed with cadmium plated screws:.
144.26.vii | 21.01 | (vii) 225 mm long x 10 mm dia. bolt.
|  |  | 8 |  |  |  | 8 | No.
[6 empty] | Total | 8 | No. | 84 | Each | 672
PWD(WB)/BUILDING WORKS/Page-140/Item-5
140.5 | 22 | Iron butt hinges of approved quality fitted and fixed with steel screws, with ISI mark.
140.5.viii | 22.01 | (viii) 100 mm x 75mm x 3.50 mm.
|  |  | 12 |  |  |  | 12 | No.
[6 empty] | Total | 12 | No. | 66 | Each | 792
PWD(WB)/BUILDING WORKS/Page-146/Item-31
146.31 | 23 | Anodised aluminium decorative handle (hexagonal / fluted) of approved quality fitted and fixed complete.
146.31.i | 23.01 | (i) 150 mm plate x 10 mm. dia rod x 12 mm. hexagonal/flutted.
|  |  | 8 |  |  |  | 8 | No.
[6 empty] | Total | 8 | No. | 87 | Each | 696
PWD(WB)/BUILDING WORKS/Page-141i/Item-10
141i.10 | 24 | (i) Iron hasp bolt of approved quality fitted and fixed complete (oxidised) with 16 mm dia rod with centre bolt and round fitting.
142i.10.b | 24.01 | (b) 250 mm long.
|  |  | 8 |  |  |  | 8 | No.
[6 empty] | Total | 8 | No. | 159 | Each | 1272
PWD(WB)/BUILDING WORKS/Page-244/Item-13-A
244.13-A | 25 | (A) Supplying Aluminium casted body hydraulic door closer as per I.S.I.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 635 | Each. | 2540
PWD(WB)/BUILDING WORKS/Page-198a/Item-5
198a.5 | 26 | Rendering the Surface of walls and ceiling with White Cement baseWATER PROOF wall putty of approved make & brand.(1.5 mm thick)
|  |  | 4 | 4.05 | 0.775 |  | 12.555 | Sq.M
|  |  | 2 | 4.6 | 0.775 |  | 7.13 | Sq.M
|  |  | 6 | 1.2 | 0.775 |  | 5.58 | Sq.M
|  |  | 2 | 2.5 | 0.775 |  | 3.875 | Sq.M
|  |  | 1 | 1.6 | 0.775 |  | 1.24 | Sq.M
|  |  | 1 | 4.35 | 4.05 |  | 17.618 | Sq.M
|  |  | -10 | 0.45 | 0.3 |  | -1.35 | Sq.M
[6 empty] | Total | 46.648 | Sq.M | 122 | Sq.M. | 5691.06
PWD(WB)/BUILDING WORKS/Page-196/Item-10
196.10 | 27 | Acrylic Distemper to interior wall, ceiling with a coat of solvent basedinterior grade acrylic primer (as per manufacturer's specification)including cleaning and smoothning of surface.Two Coats
|  |  | 4 | 4.05 | 0.775 |  | 12.555 | Sq.M
|  |  | 2 | 4.6 | 0.775 |  | 7.13 | Sq.M
|  |  | 6 | 1.2 | 0.775 |  | 5.58 | Sq.M
|  |  | 2 | 2.5 | 0.775 |  | 3.875 | Sq.M
|  |  | 1 | 1.6 | 0.775 |  | 1.24 | Sq.M
|  |  | 1 | 4.35 | 4.05 |  | 17.618 | Sq.M
|  |  | -10 | 0.45 | 0.3 |  | -1.35 | Sq.M
[6 empty] | Total | 46.648 | Sq.M | 70 | Sq.M. | 3265.36
PWD(WB)/BUILDING WORKS/Page-197/Item-17
197.17 | 28 | Protective and decorative Acrylic exterior emulsion paint of approved quality , as per manufacture specification as per direction of EIC to be apply over Acrylic primer as required. the rate included cost of material , labour scaffoldic and all incidential charges but excluding the cost of primer.In ground floor ( two coat).
197.17.a | 28.01 | (a) Normal Acrylic emulaion.
|  |  | 1 | 5.1 | 3.9 |  | 19.89 | Sq.M
|  |  | 2 | 4.55 | 3.9 |  | 35.49 | Sq.M
|  |  | 20 | 0.45 | 0.3 |  | 2.7 | Sq.M
|  |  | 10 | 1.05 | 0.075 |  | 0.788 | Sq.M
|  |  | -10 | 0.45 | 0.3 |  | -1.35 | Sq.M
|  |  | 1 | 20.5 | 0.975 |  | 19.988 | Sq.M
[6 empty] | Total | 77.506 | Sq.M | 67 | Sq.M. | 5192.9
PWD(WB)/BUILDING WORKS/Page-196/Item-8
196.8 | 29 | Applying exterior grade Acrylic primer of approved quality and brand on plaster or concrete surface old or new surface to receive decorative textured (mat finish) or smooth finish acrylic exterior emulsion paint including scraping and preparing the surface throughly complete as per manufacturer's specification and as per direction of the EIC. In Ground Floor:.
196.8.b | 29.01 | (b) two coat.
|  |  | 1 | 5.1 | 3.9 |  | 19.89 | Sq.M
|  |  | 2 | 4.55 | 3.9 |  | 35.49 | Sq.M
|  |  | 20 | 0.45 | 0.3 |  | 2.7 | Sq.M
|  |  | 10 | 1.05 | 0.075 |  | 0.788 | Sq.M
|  |  | -10 | 0.45 | 0.3 |  | -1.35 | Sq.M
|  |  | 1 | 20.5 | 0.975 |  | 19.988 | Sq.M
[6 empty] | Total | 77.506 | Sq.M | 4510 | %sqm | 3495.52
PWD(WB)/BUILDING WORKS/Page-106/Item-18
106.18 | 30 | Collapsible gate with 40 mm.X 40mm x 6 mm.Tee as top and bottom guide rail, 20 mm,X10 mm,X2 mm. vertical channels 100 mm. apart in fully stretched position 20 mm. X5 mm.M.S. flats as collapsible bracing properly rivetted and washered including 38 mm. steel rollers including locking arrangement, fitted and fixed in position with lugs set in cement concrete and including cutting necessary holes, chasing etc. in walls , floors etc. and making good damages complete. (Add extra @1% for each addl. floor upto 5th floor and @1.25% for each addl. floor above 5th floor.)In ground floor. .
|  |  | 1 | 2.3 | 4.85 |  | 11.155 | Sq.M
[6 empty] | Total | 11.155 | Sq.M | 4351 | Sq.M. | 48535.41
PWD(WB)/BUILDING WORKS/Page-104/Item-13
104.13 | 31 | (a) M.S. or W.I. ornamental grill of approved design joints continuously welded with M.S., W.I. flats and bars for windows ,railing etc. fitted and fixed with necessary screws and lugs in ground floor. (Add extra @1% for each addl. floor up to 4th floor and @1.25% for each addl. floor above 4th floor).
104.13.i | 31.01 | (i) Grill weighing above 10 kg./sq.m.and up to 16kg/sq.m.
|  |  | 10 | 0.6 | 0.45 | 0.16 | 0.432 | Cu.M
|  |  | 5 | 0.6 | 0.6 | 0.16 | 0.288 | Cu.M
|  |  | 1 | 5 | 0.9 | 0.16 | 0.72 | Cu.M
[6 empty] | Total | 1.44 | Cu.M | 10021 | Qntl. | 14430.24
PWD(WB)/BUILDING WORKS/Page-200/Item-1a
200.1a | 32 | (a) Priming one coat on steel or other metal surface with synthetic oil bound primer of approved quality including smoothening surfaces by sand papering etc.
|  |  | 1.5 | 2.3 | 2.1 |  | 7.245 | Sq.M
|  |  | 20 | 0.6 | 0.45 |  | 5.4 | Sq.M
|  |  | 5 | 0.6 | 0.6 |  | 1.8 | Sq.M
|  |  | 10 | 0.6 | 0.9 |  | 5.4 | Sq.M
[6 empty] | Total | 19.845 | Sq.M | 29 | Sq.M. | 575.51
PWD(WB)/BUILDING WORKS/Page-200/Item-2
200.2 | 33 | (A) Painting with best quality synthetic enamel paint of approved make and brand including smoothening surface by sand parpering etc. in cluding using of approved putty etc. on the surface , if necessary.
200.2.b | 33.01 | (b) On steel or other metal surface: .
200.2.b.1 | 33.02 | (1) With super gloss (hi-gloss).
201.2.b.1.iv | 33.03 | (iv) Two coats (with any shade except white).
|  |  | 1 | 5.4 | 4.85 |  | 26.19 | Sq.M
[6 empty] | Total | 26.19 | Sq.M | 79 | Sq.M. | 2069.01
PWD(WB)/BUILDING WORKS/Page-280/Item-1
280.1 | 34 | Supplying and laying true to line and level Anti-Skid, Full Body,Homogeneous & Granular finish Vitrified Tiles conforming to IS:15622-2006 & IS 4457-2007 and testing shall be made in accordance withIS:13630 [Non- modular sizes for tiles with Skid resistance > 0.5, Mohr'shardness > 5.0, Staining resistance: Class-1, Water Absorption: E <0.5%], MOR > 35 N/sq.mm in Internal area of building e.g. Toilet Block, Passage, Corridor, Accessible Open Terrace etc. set in 20 mm sand cement mortar (1:4) and 2 mm thick cement slurry at back side of tiles using cement @ 2.91 Kg./Sqm or using Polymerised Adhesive (6 mm thicklayer applied directly over finished artificial stone floor/ Mosaic etc without any backing course) laid after application slurry using 1.75 Kg of cement per Sqm below mortar only, joints grouted with admixture of white cement and colouring pigment to match with colour of tiles/ epoxy grout materials of approved make as directed and removal of wax coating of top surface of tiles wi
th warm water and polishing the tiles using soft and dry cloth upto mirror finish complete including the cost of materials, labour and all other incidental charges complete true to the manufacturer's specification and direction of Engineer-in-Charge. (White cement,synthetic adhesive and grout material to be supplied by the contractor).
280.1.b | 34.01 | b) In Ground Floor: Sizes-600 mm x600mm x10 mm with breaking strength > 1500 N
|  |  | 1 | 4.35 | 4.05 |  | 17.618 | Sq.M
[6 empty] | Total | 17.618 | Sq.M | 1589 | Sq.M. | 27995
PWD(WB)/BUILDING WORKS/Page-68/Item-39
68.39 | 35 | Supplying, fitting & fixing best quality digital printed Ceramic tiles in coloured decorative on walls and floors to match withthe existing work & 4 nos. key stones (10mm) fixed with adhesive 4.5 mm thick at the back of each tile & finishing the joints with white cement mixed with colouring oxide if required to match the colour of tiles including roughening ofconcrete surface, if necessary or by synthetic adhesive & grout materials etc. With polymerised adhesive and epoxy grout pointing including spacer - 2mm (When tiles are laid over existing hard ready surface) all complete as per direction of Engineer-in-charge.
|  |  | 2 | 4.35 | 2.1 |  | 18.27 | Sq.M
|  |  | 4 | 4.05 | 2.1 |  | 34.02 | Sq.M
|  |  | -1 | 2.05 | 2.1 |  | -4.305 | Sq.M
|  |  | 2 | 1.6 | 2.1 |  | 6.72 | Sq.M
|  |  | 2 | 1.1 | 2.1 |  | 4.62 | Sq.M
|  |  | 2 | 1.2 | 2.1 |  | 5.04 | Sq.M
|  |  | 2 | 2.5 | 2.1 |  | 10.5 | Sq.M
|  |  | -4 | 0.75 | 2.1 |  | -6.3 | Sq.M
[6 empty] | Total | 68.565 | Sq.M | 1060 | Sq.M. | 72678.9
PWD(WB)/BUILDING WORKS/Page-74/Item-47
74.47 | 36 | Supplying & laying 20 mm designer chequered titles of any shade and of approved quality as per IS: 1237: 1980 laid in patterns of as directed in pavement , footpath including necessary under lay 25 mm thick average cement motar (1:3 ) complete in all respect with all labour and materials [ using cement slurry @ 4.4 kg/sqm at back side of tiles . [ cement of motor & slurry will be supplied by the department border concrete if necessary to be paid seperately.
|  |  | 1 | 4 | 1 |  | 4 | Sq.M
[6 empty] | Total | 4 | Sq.M | 823 | Sq.M. | 3292
PWD(WB)/BUILDING WORKS/Page-62/Item-32
62.32 | 37 | Supplying, fitting & fixing granite slabs 15mm to 18 mm. thick withuniform texture & without decorative veins in columns, wall, facia etc.with 15 mm thick [avg] cement mortar (1:2) including making suitablearrangements to hold the stones properly by brass / copper hooksincluding pointing in cement mortar (1:2) (1 white cement : 2 marbledust) with admixture of pigment matching the stone shades all completeas per direction of the Engineer-in-charge including cost of all materials,labours, scaffolding, staging, curing and roughening of concrete surfacecomplete. Area of eachGranite slab ≤ 0.6 square metre.[Using cement slurry at back side of granite @ 4.4 kg/sq.m &white cement slurry for joint filling @ 1.8 kg/sq.m]
|  |  | 1 | 1.65 | 0.45 |  | 0.743 | Sq.M
|  |  | 1 | 1.8 | 0.45 |  | 0.81 | Sq.M
|  |  | 1 | 1.7 | 2.1 |  | 3.57 | Sq.M
|  |  | 1 | 1.1 | 2.1 |  | 2.31 | Sq.M
[6 empty] | Total | 7.433 | Sq.M | 2313 | Sq.M. | 17192.53
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-13
81.13 | 38 | Supplying, fitting and fixing 18 mm thick marble partition slab with chawk doongri marble square cut both side polished with two front corners rounded and edges polished.
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 1426 | Each | 4278
PWD(WB)/BUILDING WORKS/Page-243/Item-9
243.9 | 39 | Supplying bubble free float glass of approved make and brand. Conforming to IS: 2835-1987.
243.9.iv | 39.01 | (iv) 5 mm thick coloured / tinted / smoke glass.
|  |  | 10 | 0.6 | 0.45 |  | 2.7 | Sq.M
[6 empty] | Total | 2.7 | Sq.M | 585 | Sq.M. | 1579.5
PWD(WB)/BUILDING WORKS/Page-261/Item-9
261.9 | 40 | Supplying and Planting of different plant /trees ( Supplying well grown plants bushy and healthy, minimum height as specified i.e.exposed height including all leads & lift,carriage, handling, manuring, applying presticide and fertilizer etc.
261.9.i | 40.01 | i) Furcaria veriegated 10-12 leaves in height 20-30cm in earthen pots of size 25cm.
|  |  | 12 |  |  |  | 12 | No.
[6 empty] | Total | 12 | No. | 162 | Each | 1944
PWD(WB)/BUILDING WORKS/Page-261/Item-9
261.9 | 41 | Supplying and Planting of different plant /trees ( Supplying well grown plants bushy and healthy, minimum height as specified i.e.exposed height including all leads & lift,carriage, handling, manuring, applying presticide and fertilizer etc.
261.9.x | 41.01 | x) Ficus blakii ( F. Vivicon ) well branched (Bushy ) of height 120cm - 135 cm in earthen pot of size 30cm.
|  |  | 9 |  |  |  | 9 | No.
[6 empty] | Total | 9 | No. | 187 | Each | 1683
PWD(WB)/BUILDING WORKS/Page-261/Item-9
261.9 | 42 | Supplying and Planting of different plant /trees ( Supplying well grown plants bushy and healthy, minimum height as specified i.e.exposed height including all leads & lift,carriage, handling, manuring, applying presticide and fertilizer etc.
262.9.xxvi | 42.01 | xxvi) Areca Palm 4 - 5 suckers of height 90cm to 105 cm in earthen pots of size 25 cm.
|  |  | 6 |  |  |  | 6 | No.
[6 empty] | Total | 6 | No. | 127 | Each | 762
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-79/Item-4
79.4 | 43 | Supplying, fitting and fixing Orissa pattern water closet in white glazed vitreous chinaware of approved make in position complete excluding 'P' or 'S' trap (excluding cost of concrete for fixing).
79.4.i | 43.01 | 580 mm X 440 mm.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 1613 | Each | 6452
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-10
81.10 | 44 | Supplying, fitting and fixing Closet seat of approved make with lid and C.P. hinges, rubber buffer and brass screws supplied, fitted and fixed complete.
81.10.b | 44.01 | Anglo-Indian .
81.10.b.i |  | Plastic (hallow type) black.
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-80/Item-6
80.6 | 45 | Supplying, fitting and fixing Flat back urinal (half stall urinals) in white vitreous chinaware of approved make in position with brass screws on 75 mm X 75 mm X 75 mm wooden blocks complete.
80.6.i | 45.01 | 635mm X 395mm X 420mm
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 2869 | Each | 8607
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-80/Item-7
80.7 | 46 | Supplying, figging and fixing Squating plate with integral flushing in white vitreous chinaware of approved make in cement concrete(6:3:1) with jhama chips complete.(Payment of concrete will be paid seperately).
80.7.i | 46.01 | 450 mm X 350 mm.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 881 | Each | 1762
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-36/Item-1
36.1 | 47 | Supplying, fitting and fixing 10 litre porcelian low-down cistern of approved make without fitting and brackets.White.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 2297 | Each | 9188
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-11
81.11 | 48 | Supplying, fitting and fixing 32 mm dia. flush pipe of approved make with necessary fixing materials and clamps complete.
81.11.i | 48.01 | Polythene Flush Pipe.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 155 | Each | 620
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-12
81.12 | 49 | Supplying, fitting and fixing urinals flush pipe fittings of approved brand.
81.12.a | 49.01 | C.P. urinals flush pipe fiitngs range of one .
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 414 | Each | 1242
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-41/Item-2
41.2 | 50 | Supplying, fitting and fixing white vitreous china best quality approved make wash basin with C.I. Brackets on 75 mm X 75mm wooden blocks, C.P. waste fittings of 32 mm dia., one approved quality brass C.P. pillar cock of 15 mm dia., C.P. chain with rubber plug of 30mm dia, approved quality P.V.C.waste pipe with C.P. nut 32mm dia., 900 mm long approved quality P.V.C. connection pipe with heavy brass C.P.nut including mending good all damages and painting the brackets with two coats of approved paint.
41.2.iii | 50.01 | 630 mm x 450 mm size.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 3260 | Each | 6520
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-43/Item-9
43.9 | 51 | Supplying, fitting & fixing approved brand P.V.C. CONNECTOR white flexible, with both ends coupling with heavy brass C.P.nut, 15mm dia.
43.9.iii | 51.01 | 600 mm long.
|  |  | 7 |  |  |  | 7 | No.
[6 empty] | Total | 7 | No. | 107 | Each | 749
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-43/Item-10
43.10 | 52 | Supplying, fitting and fixing approved brand 32mm dia P.V.C. waste pipe, with PVC coupling at one end fitted with necessary clamps.
43.10.iv | 52.01 | 1050mm long.
|  |  | 7 |  |  |  | 7 | No.
[6 empty] | Total | 7 | No. | 91 | Each | 637
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-3/Item-3
3.3 | 53 | Supplying, fitting and fixing shower of approved brand and make.
3.4.f | 53.01 | Hand shower(Health Faucet) with 1mtr Fexible Tube with wall Hook (Equivalent to code No.573 & Model-ALLIED of Jaquar or Similar)
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 1251 | Each | 5004
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-6/Item-7
6.7 | 54 | Supplying, fitting and fixing bib cock or stop cock.
6.7.a-ii | 54.01 | Chromium plated Bib Cock long body with wall flange with aerator (Equivelent to Code No.512 & Model- Tropical /sumthing special of ESSCO or Similar brand).
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 659 | Each | 2636
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-6/Item-7
6.7 | 55 | Supplying, fitting and fixing bib cock or stop cock.
6.7.b-i | 55.01 | Chromium plated Stop Cock (Equivelent to Code No.513(A) & 513(B) Model- Tropical /sumthing special of ESSCO or Similar brand).
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 493 | Each | 1972
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-3/Item-3
3.3 | 56 | Supplying, fitting and fixing shower of approved brand and make.
3.3.a-ii | 56.01 | Chromium plated round shower with revolving joint (Equivalent to Code No.541(N) & Model - Tropical / Sumthing special of ESSCO or Similar Brand).
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 360 | Each | 720
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-3/Item-3
3.3 | 57 | Supplying, fitting and fixing shower of approved brand and make.
3.4.a-iii | 57.01 | Chromium plated round shower arm 190 mm long (Equivalent to Code No.536(A) & Model - Tropical / Sumthing special of ESSCO or Similar Brand).
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 309 | Each | 618
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-6/Item-7
6.7 | 58 | Supplying, fitting and fixing bib cock or stop cock.
6.7.d-i | 58.01 | Chromium plated plated angular Stop Cock with wall flange (Equivelent to Code No.5053 & Model- Florentine of Jaquar or Similar brand).
|  |  | 12 |  |  |  | 12 | No.
[6 empty] | Total | 12 | No. | 815 | Each | 9780
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-45/Item-19
45.19 | 59 | Supplying, fitting and fixing pillar cock of approved make.
45.19-a.i | 59.01 | CP Pillar Cock-15 mm. (Equivalent to Code No.507 & Model-Tropical/Sumthing Special of ESSCO or similar brand).
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 555 | Each | 1110
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-12/Item-19-I
12.19-I | 60 | Supplying, fitting and fixing PVC pipes of approved make of of Schedule 80 (medium duty) conforming to ASTMD-1785 and threaded to match with GI Pi;es as per IS:1239 (Part-I) with all necessary accessories, specials viz. socket, bend, tee, union, cross, elbo, nipple, longscrew, reducing socket, reducing tee, short piece etc. fitted with holder bats clamps, including cutting piles, making threads, fitting, fixing etc. complete in all respect including cost of all necessary fittings as required, jointing materials and two coats of painting with approved paint in any position above ground. (Payment will be made on the centre line measurements of total pipe line including all specials. No separate payment will be made for accessories, specials. Payment for painting will be made seperately).
12.19-1.a | 60.01 | For Exposed Work PVC Pipes.
12.19-1.a.iii | 60.02 | 25 mm.
|  |  | 1 | 35 |  |  | 35 | M
[6 empty] | Total | 35 | M | 177 | Mtr. | 6195
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-12/Item-19-I
12.19-I | 61 | Supplying, fitting and fixing PVC pipes of approved make of of Schedule 80 (medium duty) conforming to ASTMD-1785 and threaded to match with GI Pi;es as per IS:1239 (Part-I) with all necessary accessories, specials viz. socket, bend, tee, union, cross, elbo, nipple, longscrew, reducing socket, reducing tee, short piece etc. fitted with holder bats clamps, including cutting piles, making threads, fitting, fixing etc. complete in all respect including cost of all necessary fittings as required, jointing materials and two coats of painting with approved paint in any position above ground. (Payment will be made on the centre line measurements of total pipe line including all specials. No separate payment will be made for accessories, specials. Payment for painting will be made seperately).
12.19-1.a | 61.01 | For Exposed Work PVC Pipes.
12.19-1.a.i | 61.02 | 15 mm dia.
|  |  | 1 | 20 |  |  | 20 | M
[6 empty] | Total | 20 | M | 101 | Mtr. | 2020
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-12/Item-19-I
12.19-I | 62 | Supplying, fitting and fixing PVC pipes of approved make of of Schedule 80 (medium duty) conforming to ASTMD-1785 and threaded to match with GI Pi;es as per IS:1239 (Part-I) with all necessary accessories, specials viz. socket, bend, tee, union, cross, elbo, nipple, longscrew, reducing socket, reducing tee, short piece etc. fitted with holder bats clamps, including cutting piles, making threads, fitting, fixing etc. complete in all respect including cost of all necessary fittings as required, jointing materials and two coats of painting with approved paint in any position above ground. (Payment will be made on the centre line measurements of total pipe line including all specials. No separate payment will be made for accessories, specials. Payment for painting will be made seperately).
12.19-1.b | 62.01 | For Concealed Work.
12.19-1.b.i | 62.02 | 15 mm.
|  |  | 1 | 20 |  |  | 20 | M
[6 empty] | Total | 20 | M | 137 | Mtr. | 2740
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-5/Item-5
5.5 | 63 | Supplying, fitting and fixing gunmetal wheel valve of approved brand and make tested to 21 kg sq.cm. (for water lines only).
5.5.vii | 63.01 | 25 mm.
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 778 | Each | 2334
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-37/Item-6
37.6 | 64 | Supplying PVC water storage tank of approved quality with closed top weith lid (Black) - Multilayer.
37.6.b | 64.01 | 1000 litre capacity.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 5128 | Each | 10256
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-37/Item-10
37.10 | 65 | Labour for hoisting plastic water storage tank.
37.10.i | 65.01 | Upto 1500 litre capacity.
37.10.i.a | 65.02 | Upto 1st story from G.L.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 96 | Each | 192
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-38/Item-13
38.13 | 66 | Labour for punching hole in plastic water storage tank upto 50 mm dai.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 19 | Each | 76
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 67 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
68.23-A.i | 67.01 | Single socketed 3 meter length.
69.23-A.i.b | 67.02 | 110 mm.
|  |  | 1 | 30 |  |  | 30 | M
[6 empty] | Total | 30 | M | 292 | Mtr. | 8760
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 68 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 68.01 | Fittings.
70.23.B.ii | 68.02 | Plain tee.
70.23.B.ii.b |  | 110 mm.
|  |  | 12 |  |  |  | 12 | No.
[6 empty] | Total | 12 | No. | 85 | Each | 1020
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 69 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 69.01 | Fittings.
70.23.B.i | 69.02 | Coupler.
70.23.B.i.b | 69.03 | 110 mm.
|  |  | 15 |  |  |  | 15 | No.
[6 empty] | Total | 15 | No. | 85 | Each | 1275
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 70 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 70.01 | Fittings.
70.23.B.iii | 70.02 | Door Tee.
70.23.B.iii.b |  | 110 mm.
|  |  | 9 |  |  |  | 9 | No.
[6 empty] | Total | 9 | No. | 195 | Each | 1755
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 71 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 71.01 | Fittings.
71.23.B.ix | 71.02 | Bend 45o.
71.23.B.ix.b |  | 110 mm.
|  |  | 9 |  |  |  | 9 | No.
[6 empty] | Total | 9 | No. | 89 | Each | 801
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 72 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 72.01 | Fittings.
71.23.B.xi | 72.02 | Door Bend (T.S).
71.23.B.xi.b |  | 110 mm.
|  |  | 7 |  |  |  | 7 | No.
[6 empty] | Total | 7 | No. | 147 | Each | 1029
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 73 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 73.01 | Fittings.
71.23.B.xvi | 73.02 | Pipe Clip.
71.23.B.xvi.b |  | 110 mm.
|  |  | 30 |  |  |  | 30 | No.
[6 empty] | Total | 30 | No. | 21 | Each | 630
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 74 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 74.01 | Fittings.
71.23.B.xvii | 74.02 | W.C. Connector (150m m long) 125 X 110 (W/WC Ring) 75 mm. .
|  |  | 6 |  |  |  | 6 | No.
[6 empty] | Total | 6 | No. | 142 | Each | 852
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 75 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 75.01 | Fittings.
72.23.B.xxxi | 75.02 | Plain Floor Trap with Top tile and Stainer. 75mm..
|  |  | 6 |  |  |  | 6 | No.
[6 empty] | Total | 6 | No. | 144 | Each | 864
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 76 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 76.01 | Fittings.
73.23.B.l | 76.02 | Rubber Ring.
73.23.B.l.b | 76.03 | 110 mm.
|  |  | 30 |  |  |  | 30 | No.
[6 empty] | Total | 30 | No. | 17 | Each | 510
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 77 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
74.23.C | 77.01 | Rubber Lubricant. 500 ML.
|  |  | 5 |  |  |  | 5 | No.
[6 empty] | Total | 5 | No. | 187 | Each | 935
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 78 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
74.23.D | 78.01 | Solvent Cement. 250 ML.
|  |  | 5 |  |  |  | 5 | No.
[6 empty] | Total | 5 | No. | 103 | Each | 515
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-74/Item-24
74.24 | 79 | Labour for fitting and fixing U.P.V.C. pipes for above ground work including cost of jointing materials etc. fitting and fixing all necessary specials, cutting pipes, cutting holes in walls or R.C. floor where necessary and mending good all damages excluding the cost of masonry or concrete work, if necessary, but including the cost and fitting and fixing holder bat clamps (any foor) or for underground work including cutting trenches upto 1.5 metre and refilling the same complete as per direction of the Enginer-in-charge) Payment will be made on centre line measurement of the total pipeline including specials.).
74.24.B | 79.01 | Underground.
74.24.B.ii |  | 110 mm dia.
|  |  | 1 | 30 |  |  | 30 | M
[6 empty] | Total | 30 | M | 84 | metre | 2520
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-87/Item-1
87.1 | 80 | Constructing Inspection pit of inside measurement 600mm X 600mm X upto 600mm(depth) with 250 mm thick 1st. class brick work in cement mortar(4:1) on all sides, bottom of the pit consisting of 100 mm thick cement concrete(1:6:3) with stone chips over a layer of jhama brick flat soiling, 15 mm thick (1:4) cement plaster to inside walls and outside walls upto G.L. and 20 mm thick(1:4) plaster to bottom of the pit, providing necessary invert with cement concrete(1:3:6) with stone chips as per direction, neat cement finishing to entire internal surfaces, top of the pit covered with 100mm thick R.C.C. slab (1:1.5:3) with stone chips and necessary reinforcements upto 1% and shuttering including 6 mm thick cement plaster(1:4) in all external surfaces of the slab and one 560 mm dia. R.C.C. manhole cover of approved make supplied, fitted and fixed in the slab with necessary fittings, necessary earthwork in excavation in all sorts of soil, filling sides of the pit with earth and removing spoils
after work complete in all respect with all costs of labour and materials.
87.1.ii | 80.01 | With Bazree (Pakur Variety).(SAIL/TATA/RINL)
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 6434 | each | 19302
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-88/Item-3
88.3 | 81 | Construction of Septic tank of different capacities as per approved drawing with 1st class brick work in cement mortar (4:1) including two 560 mm dia. R.C.C. manhloe cover of approved make supplied, fitted and fixied in the top slab with necessary fittings, 19 mm thick cement plaster(4:1) with neat cement finish to the internal surfaces and 12 mm thick plaster(4:1) to outside wall upto 200 mm below G.L. floor finished with 25 mm thick grey artificial stone including supplying, fitting and fixing all necessary specials, fittings, S.W. tees, C.I. foot rest etc. including excavating earth in all sorts of soil, shoring, bailing and pumping out water as necessary, ramming, dressing the bed and refilling the sides of the tank with earth, removing spoils, fliing up the chamber with clear water, removing foreign materialsfrom the chamber and including constructing attached inspection pit as per approved dawing and connecting all necessary pipes, joints etc. with internal plaster work and artif
icial stone flooring is to be done with admixture of water proofing compound @ 5% by weight of cement, complete in all respect as per directon of Engineer-in-Charge.
89.3.iv | 81.01 | For 50 users.
89.3.iv.B |  | With Pakur variety.(SAIL/TATA/RINL)
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 81946 | Each | 81946
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-89/Item-4
89.4 | 82 | Construction of circular soak well 2.5 metre deep in all types of sandy soils with dry brick work upto 1.6 metre from the bottom having 150 mm intermediate cement brick work(6:1) band all round and cement brick work(6:1) upto 0.90 metre from top with 19 mm thick cement plastering(4:1) to inside face upto the depth of cement brick work, 12 mm thick cement plaster(4:1) on top of the R.C.C. cover slab including filling bottom 1.00 metre of inside of the well with brick metal(50 mm to 63 mm size) including R.C.C. cover slab of designed thickness with cement concrete(4:2:1) with stone chips with necessary reinforcement and shuttering including one 560 mm dia. R.C.C. manhole cover of approved make supplied, fitted and fixed in the cover slab with necessary fittings, making necessary arrangements for pipe conections, excavation of well including shoring, dewatering and remeving the excess earth from the premisis as per direction complete in all respect with all costs of labour and materials.W
ith 250 mm thick dry brick work and 250 mm thick cement brick work(6:1) and 1.00 m. inside dia.
89.4.A | 82.01 | (SAIL/TATA/RINL)
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 15532 | Each | 15532
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-82/Item-22
82.22 | 83 | Supplying, fitting and fixing towel rail with two brackets.
82.22.a | 83.01 | C.P. over brass.
82.22.a.ii | 83.02 | 25 mm dia. and 600 mm long.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 430 | Each | 1720
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-37/Item-8
37.8 | 84 | Supplying, fitting and fixing cast iron raised rain proof tank cover 500 mm dai. With locking arrangements(weighing not less than 12 kg).
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 1263 | Each | 1263
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-15
81.15 | 85 | Supplying, fitting and fixing bevelled edge mirror 5.5 mm thick silver red as per I.S. 3438/1965 together with brass C.P. hinges.
81.15.ii | 85.01 | 600 mm X 450 mm.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 484 | Each | 1936
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-82/Item-18
82.18 | 86 | Supplying, fitting and fixing soap holder.
82.18.b | 86.01 | Fibre glass.
|  |  | 16 |  |  |  | 16 | No.
[6 empty] | Total | 16 | No. | 58 | Each | 928
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-83/Item-23
83.23 | 87 | Supplying, fitting and fixing procelain toilet paper holder of approved make with wooden spindle as necessary.
83.23.i | 87.01 | Roll type size 250 mm X 125 mm.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 293 | Each | 1172
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-16
81.16 | 88 | Supplying, fitting and fixing glass shelf with aluminium guard rails.
81.16.a | 88.01 | Ordinary type with 5.5 mm sheet glass.
82.16.a.i | 88.02 | 450 mm X 125 mm.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 341 | Each | 1364
[6 empty] | TOTAL AMOUNT |  |  |  |  | 874017.91
[6 empty] | 18 | % GST on Total Amount |  |  |  | 157323.22
[6 empty] | Sub - Total 1 (Total Amount + GST) |  |  |  |  | 1031341.13
[6 empty] | 3 | % Contigency on Sub-Total 1 |  |  |  | 30940.23
[6 empty] | Sub - Total 2 (Sub - Total 1 + contigency) |  |  |  |  | 1062281.36
[6 empty] | Labour Welfare Cess 1% on Sub-Total 1 |  |  |  |  | 10313.41
[6 empty] | Grand total |  |  |  |  | 1072594.77
[6 empty] | Say |  |  |  |  | 1072595
(Rupees ten lakh eighteen thousand fifty six) only